Remaining Grant Timeline

| Date | Responsible Party | Action |
| --- | --- | --- |
| February 12 | Grantee | Maps & narratives due to DNR |
| February 19 | Grantee | Information due to Wildlife Resources Division |
| February 26 | Grantee | Information due to State Historic Preservation Division |
| February- TBD | DNR | Formal application workshop 24th 1- 3:30 pm 25th 9- 11:30 am |
| March-April | DNR | Pre-award Inspections completed |
| April 30 | Grantee | Application packets due to DNR |
| May-June | DNR | DNR review paperwork & prepares package for submittal to NPS |
| July-Sept | NPS | NPS review of grant package |
| October | NPS | NPS approval of grant package |
| November | DNR | Financial workshop & grant agreement |